## Operations
Operation inventory
Illustrative data. Counts come from direct connections on Relationships.
Operation | Calls count | Callers count | Build wave | Cycle group
GetCustomer | 0 | 3 | 1 | None
ValidateTransfer | 1 | 1 | 2 | None
GetAccountSummary | 1 | 0 | 2 | None
TransferFunds | 2 | 0 | 3 | None

## Relationships
Direct operation relationships
Filter Caller for outgoing calls. Filter Called operation for incoming callers.
Caller | Called operation | Relationship
ValidateTransfer | GetCustomer | Calls
GetAccountSummary | GetCustomer | Calls
TransferFunds | ValidateTransfer | Calls
TransferFunds | GetCustomer | Calls
Source: invented example from operation-migration-example.md. No real Composer data.

## Migration Plan
Implementation and Composer retirement
Build dependencies first. Keep old implementations until callers and incoming traffic have moved.
Build wave | Operation | Implement after | Native implementation | Composer removal condition
1 | GetCustomer | None | Not started | All three callers no longer need it; direct traffic moved.
2 | ValidateTransfer | GetCustomer | Not started | TransferFunds no longer needs it; direct traffic moved.
2 | GetAccountSummary | GetCustomer | Not started | Incoming traffic moved; no remaining Composer callers.
3 | TransferFunds | ValidateTransfer, GetCustomer | Not started | Incoming traffic moved; no remaining Composer callers.