## Migration Plan
Operation implementation order
Dependencies first. Cycles require coordinated implementation; blank waves have unresolved dependencies.
Build wave | Channel | Operation | Implement after (direct) | Cycle group | Issue
1 | INTERNET | GetAccountDetailsOp | None | None
1 | INTERNET | GetClientAccountsOp | None | None
1 | INTERNET | GetClientLinksOp | None | None
1 | INTERNET | TransferFundsOp | None | None
2 | INTERNET | ValidateClientLinksOp | INTERNET/GetClientLinksOp | None
3 | INTERNET | GetClientOverviewOp | INTERNET/GetClientLinksOp INTERNET/ValidateClientLinksOp | None

## Operations
Operation inventory
Counts are unique direct operation connections, not step counts or implementation effort.
Channel | Operation | Calls count | Callers count | Build wave | Cycle group
INTERNET | GetAccountDetailsOp | 0 | 0 | 1 | None
INTERNET | GetClientAccountsOp | 0 | 0 | 1 | None
INTERNET | GetClientLinksOp | 0 | 2 | 1 | None
INTERNET | GetClientOverviewOp | 2 | 0 | 3 | None
INTERNET | TransferFundsOp | 0 | 0 | 1 | None
INTERNET | ValidateClientLinksOp | 1 | 1 | 2 | None